## Phase 1
S.No | Module | Total Number of Test Cases |  | # of Test Cases Automated | # of Test Cases not part of Automation | # of Test Scripts In Progress | Planned Target date to complete TC’s | Revised Target date to complete TC’s
1 | Konzernview | Planned | 28 | 28 | 19 - Flow needs to be modified | 3 | July/27/2016
33 – Not an automation candidate
23-Anteil field is disabled
|  | Actual | 33 |  | Kenzern view-19,23,24,29,33 |  |  | Sep/13/2016
2 | Partner Search | Planned | 6 | 25 | 27 – IAS Test Case | 1 | Aug/12/2016
23 - UCS Linkage
|  | Actual | 28 |  | 24 – UCS Linkage |  |  | Sep/16/2016
4 | International Address | Planned | 10 | - | - | -
|  | Actual | 10 |  | -
5 | Partner Creation | Planned | 10 | 14 | 1– UCS Linkage | - | Aug/26/2016
|  | Actual | 15 |  | -
| Partner Modification | Planned | 29 | 34 | 1 – UCS Linkage | 2 | Sept/23/2016
6 |  |  |  |  | 2 – UCS Linkage
|  | Actual | 37 |  | 29-Pending |  |  | Oct/26/2016
| TOTAL |  | 123 | 101 | 8 | 6

## Phase 2
S.No | Module | Total Number of Test Cases |  | # of Test Cases Automated | # of Test Cases not part of Automation/Comments | # of Test Scripts In Progress | Planned Target date to complete TC’s | Revised Target date to complete TC’s
1 | Admin Screens | Planned | 33 | 33 | #TC 32,33 - Raised defect,Scripting completed, execution pending |  | December/12/2016
|  | Actual | 33 |  |  |  | December/10/2016
2 | User Admin | Planned | 17 | 21 | Test cases scripting done and uploaded to ALM |  | May/19/2017
|  | Actual | 21
3 | Global Printing | Planned | 10 | 15 | Test cases scripting done and uploaded to ALM |  | June/9/2017
|  | Actual | 15
4 | Bank Account process | Planned | 35
Actual
| Mandate Process and posting | Planned | 62
5
Actual
6 | International Address | Planned | 10
|  | Actual | 10
| TOTAL |  | 167 | 69