## Scope
SCOPE for UPM Automation
Regression automation of UPM Application for DL16.B release
Test cases planned -250
Tool - Selenium

## Project Plan-UPM
UPM Test Automation PLAN
S.No | Automation Task | Description | Responsibility | Planned effort | Planned Start Date | Planned End Date | Revised Effort | Revised start date | Revised end date | Actual Effort | Actual Start Date | Actual End Date | Completion % | Status | Deliverables | Comments
1 | Planning | Identification of Resources | Poongodi |  | 2016-04-18 | 2016-04-19 |  |  |  |  | 2016-04-18 | 2016-04-19 |  | Completed
|  | Test environment Set up(Access to UCS application Latest version) | Poongodi |  | 2016-04-18 | 2016-04-19 |  |  |  |  | 2016-04-18 | 2016-04-19 |  | Completed
|  | Access to allocated machines with credentials | Poongodi |  | 2016-04-18 | 2016-04-19 |  |  |  |  | 2016-04-18 | 2016-04-19 |  | Completed
|  | License procurement of UFT tool(QC Integration) | Poongodi |  | 2016-04-18 | 2016-04-19 |  |  |  |  | 2016-04-18 | 2016-04-19 |  | Completed
2 | Initialization | Installation of UFT and related tools | Automation |  | 2016-04-18 | 2016-04-19 |  |  |  |  | 2016-04-18 | 2016-04-19 |  | Completed
|  | Identification of business cases for automation | Venkat/Bhargav |  | 2016-04-18 | 2016-04-22 |  |  |  |  | 2016-04-18 | 2016-04-22 |  | Completed
|  | Test case walkthrough/Clarifications resolution (If required for the identified business scenarios) | Gurinder/Venkat/Bhargav |  | 2016-04-18 | 2016-04-22 |  |  |  |  | 2016-04-18 | 2016-04-22 |  | Completed
|  | Framework Implementation | Automation |  | 2016-04-18 | 2016-04-29 |  |  |  |  | 2016-04-18 | 2016-04-29 |  | Completed
3 | Test cases identification & Partner creation | Identification of business cases for automation for RPCC | Gurinder |  | 2016-04-22 | 2016-04-22 | [7 empty] | Completed | 1. Test data sheets 2. Automation test scripts 3. Results and screenshots(if applicable) for the test cases
|  | Updation of manual test cases | Gurinder |  | 2016-04-25 | 2016-04-29 | [7 empty] | Completed
|  | Framework enhancement based on the identified scenarios(On Going process) | Venkat/Bhargav |  | 2016-05-02 | 2016-05-06 |  |  |  |  | 2016-05-16 |  |  | Completed
|  | Customization of the data sheet for automation | Venkat/Bhargav |  | 2016-05-02 | 2016-05-06 |  |  |  |  | 2016-05-16 |  |  | Completed
|  | Preparation of test scripts | Venkat/Bhargav |  | 2016-05-02 | 2016-05-06 |  |  |  |  | 2016-05-16 |  |  | Completed
|  | Dry Run of the test cases | Venkat/Bhargav |  | 2016-05-02 | 2016-05-06 |  |  |  |  | 2016-05-16 |  |  | Completed
4 | Test cases identification & Crefo search | Identification of business cases for automation for RPCC | Gurinder |  | 2016-04-22 | 2016-04-22 | [7 empty] | WIP | 1. Test data sheets 2. Automation test scripts 3. Results and screenshots(if applicable) for the test cases
|  | Updation of manual test cases | Gurinder |  | 2016-04-25 | 2016-04-29 | [7 empty] | WIP
|  | Framework enhancement based on the identified scenarios(On Going process) | Venkat/Bhargav |  | 2016-05-02 | 2016-05-06 |  |  |  |  | 2016-05-16 |  |  | YTS
|  | Customization of the data sheet for automation | Venkat/Bhargav |  | 2016-05-02 | 2016-05-06 |  |  |  |  | 2016-05-16 |  |  | YTS
|  | Preparation of test scripts | Venkat/Bhargav |  | 2016-05-02 | 2016-05-06 |  |  |  |  | 2016-05-16 |  |  | YTS
|  | Dry Run of the test cases | Venkat/Bhargav |  | 2016-05-02 | 2016-05-06 |  |  |  |  | 2016-05-16 |  |  | YTS
5 | Test cases identification & Partner modification | Identification of business cases for automation for RPCC | Gurinder |  | 2016-05-02 | 2016-05-06 |  |  |  |  | 2016-05-16 |  |  | YTS | 1. Test data sheets 2. Automation test scripts 3. Results and screenshots(if applicable) for the test cases
|  | Updation of manual test cases | Gurinder |  | 2016-05-02 | 2016-05-06 |  |  |  |  | 2016-05-16 |  |  | YTS
|  | Framework enhancement based on the identified scenarios(On Going process) | Venkat/Bhargav |  | 2016-05-09 | 2016-05-27 |  |  |  |  | 2016-05-23 |  |  | YTS
|  | Customization of the data sheet for automation | Venkat/Bhargav |  | 2016-05-09 | 2016-05-27 |  |  |  |  | 2016-05-23 |  |  | YTS
|  | Preparation of test scripts | Venkat/Bhargav |  | 2016-05-09 | 2016-05-31 |  |  |  |  | 2016-05-23 |  |  | YTS
|  | Dry Run of the test cases | Venkat/Bhargav |  | 2016-05-09 | 2016-05-31 |  |  |  |  | 2016-05-23 |  |  | YTS
6 | Test cases identification & enhancement- Master data posting | Identification of business cases for automation for RPCC | Gurinder |  | 2016-05-02 | 2016-05-06 | [7 empty] | YTS | 1. Test data sheets 2. Automation test scripts 3. Results and screenshots(if applicable) for the test cases
|  | Updation of manual test cases | Gurinder |  | 2016-05-02 | 2016-05-06 | [7 empty] | YTS
5 |  | Framework enhancement based on the identified scenarios(On Going process) | Venkat/Bhargav |  | 2016-05-09 | 2016-06-17 |  |  |  |  | 2016-05-23 |  |  | YTS
|  | Customization of the data sheet for automation | Venkat/Bhargav |  | 2016-05-09 | 2016-06-17 |  |  |  |  | 2016-05-23 |  |  | YTS
|  | Preparation of test scripts | Venkat/Bhargav |  | 2016-05-09 | 2016-06-17 |  |  |  |  | 2016-05-23 |  |  | YTS
|  | Dry Run of the test cases | Venkat/Bhargav |  | 2016-05-09 | 2016-06-17 |  |  |  |  | 2016-05-23 |  |  | YTS
7 | Test cases identification & enhancement- partner consolidation | Identification of business cases for automation for RPCC | Gurinder |  | 2016-05-09 | 2016-05-13 |  |  |  |  | 2016-05-23
|  | Updation of manual test cases | Gurinder |  | 2016-05-09 | 2016-05-13 |  |  |  |  | 2016-05-23
|  | Framework enhancement based on the identified scenarios(On Going process) | Venkat/Bhargav |  | 2016-06-20 | 2016-07-15
|  | Customization of the data sheet for automation | Venkat/Bhargav |  | 2016-06-20 | 2016-07-15
|  | Preparation of test scripts | Venkat/Bhargav |  | 2016-06-20 | 2016-07-15
|  | Dry Run of the test cases | Venkat/Bhargav |  | 2016-06-20 | 2016-07-15
8 | Test cases identification & enhancement- Mandate Process and posting | Identification of business cases for automation for RPCC | Gurinder |  | 2016-05-16 | 2016-05-20
|  | Updation of manual test cases | Gurinder |  | 2016-05-16 | 2016-05-20
|  | Framework enhancement based on the identified scenarios(On Going process) | Venkat/Bhargav |  | 2016-07-18 | 2016-08-19
|  | Customization of the data sheet for automation | Venkat/Bhargav |  | 2016-07-18 | 2016-08-19
|  | Preparation of test scripts | Venkat/Bhargav |  | 2016-07-18 | 2016-08-19
|  | Dry Run of the test cases | Venkat/Bhargav |  | 2016-07-18 | 2016-08-19
9 | ReleaseDL16.B changes incorporation in automation & Closure | Execution of developed test cases in DL15.B SIT environment | Venkat/Bhargav |  | 2016-08-22 | 2016-09-03 | [7 empty] | YTS
|  | Test script should be changed according to the new changes implemented in ReleaseDL16.B | Venkat/Bhargav |  | 2016-09-05 | 2016-09-16
10 | Test execution in SIT Regression of DL16.B | Execution of automated testacase cases. Collating of test execution results and reporting Re-execution on need basis | Venkat/Bhargav |  | 2016-10-10 | 2016-10-20 | [7 empty] | YTS

## Milestone plan
Release | Start | End | Remarks
SIT | 06.09.2016 | 21.10.2016
UAT | 24.10.2016 | 02.12.2016
PTO | 05.12.2016 | 09.12.2016

## Issues and Risks
Issues and Risks
Application | Description | Type | Proposed Solution | Owner | Due Date (dd/mm/yy) | Status
UPM | Test Execution alone is automated with limited check points verification. Complete end to end verification is not automated at the moment | Risk |  | Hexaware
UPM | Test case updating activity should be done prior to automation script capturing. If this getting delayed automation progress will be impacted | Risk |  | Hexaware
UPM | External interfaces are not covered in automation | Risk |  | Hexaware

## Resources
Resource Plan
Resource | Start Dt | End Dt | May | June | July | Aug | Sep | Oct | Total in PDS | Leave expected | Remarks
Venaktesh B | 2016-05-02 | 2016-10-31 | 22 | 22 | 22 | 22 | 22 | 22 | 110 | 9.75
Bhargav S | 2016-05-02 | 2016-10-31 | 22 | 22 | 22 | 22 | 22 | 22 | 110 | 9.75
Gurinder and Shamini | [10 empty] | For manual testing support
[7 empty] | Total PD's |  | 220 | 19.5
Total avaialble | [8 empty] | 200.5
Total planned

## Legend
General rules:
1 | DO NOT delete any columns. if a column is not used by you HIDE it
2 | There are formulas to calculate % completion, open effort.
3 | update the PP every week (min. 1 time)
4 | save the new version with a date in the name e.g. 'UCS_Project_Plan_Rel2013_1_D20130414.xls'
5 | Atleast maintain 5 weeks of archive PPs so that we can have 1 month old data as well.
6 | always update the 'last update date' in the excel ROW #1
7 | add new rows for new tasks coming up and put the planned, revised, actual efforts
8 | all resources working in your project temporarily or long term should be covered.
9 | initially put PLANNED effort column & REVISED effort cols. same values.
10 | In case of revision in effort or dates, update the Revised columns only. DO not touch the planned columns.
11 | this plan you can use for BWSR & Dashboard reporting. Will be useful for Praveen & Alok to identify free capacity.
12 | Important: all planned / revised schedules (milestone dates) MUST be approved by DL-OrgIT in written form.

## Sheet1
UPM Test Automation PLAN
S.No | Automation Task | Description | Responsibility | Planned effort | Planned Start Date | Planned End Date | Revised Effort | Revised start date | Revised end date | Actual Effort | Actual Start Date | Actual End Date | Completion % | Status | Deliverables | Comments
1 | Planning | Identification of Resources | Poongodi |  | 2016-04-18 | 2016-04-19 |  |  |  |  | 2016-04-18 | 2016-04-19 |  | Completed
|  | Test environment Set up(Access to UCS application Latest version) | Poongodi |  | 2016-04-18 | 2016-04-19 |  |  |  |  | 2016-04-18 | 2016-04-19 |  | Completed
|  | Access to allocated machines with credentials | Poongodi |  | 2016-04-18 | 2016-04-19 |  |  |  |  | 2016-04-18 | 2016-04-19 |  | Completed
|  | License procurement of UFT tool(QC Integration) | Poongodi |  | 2016-04-18 | 2016-04-19 |  |  |  |  | 2016-04-18 | 2016-04-19 |  | Completed
2 | Initialization | Installation of UFT and related tools | Automation |  | 2016-04-18 | 2016-04-19 |  |  |  |  | 2016-04-18 | 2016-04-19 |  | Completed
|  | Identification of business cases for automation | Venkat/Bhargav |  | 2016-04-18 | 2016-04-22 |  |  |  |  | 2016-04-18 | 2016-04-22 |  | Completed
|  | Test case walkthrough/Clarifications resolution (If required for the identified business scenarios) | Gurinder/Venkat/Bhargav |  | 2016-04-18 | 2016-04-22 |  |  |  |  | 2016-04-18 | 2016-04-22 |  | Completed
|  | Framework Implementation | Automation |  | 2016-04-18 | 2016-04-29 |  |  |  |  | 2016-04-18 | 2016-04-29 |  | Completed
3 | Test cases identification & Partner creation | Identification of business cases for automation for RPCC | Gurinder |  | 2016-04-22 | 2016-04-22 | [7 empty] | Completed | 1. Test data sheets 2. Automation test scripts 3. Results and screenshots(if applicable) for the test cases
|  | Updation of manual test cases | Gurinder |  | 2016-04-25 | 2016-04-29 | [7 empty] | Completed
|  | Framework enhancement based on the identified scenarios(On Going process) | Venkat/Bhargav |  | 2016-05-02 | 2016-05-06 |  |  |  |  | 2016-05-16 |  |  | Completed
|  | Customization of the data sheet for automation | Venkat/Bhargav |  | 2016-05-02 | 2016-05-06 |  |  |  |  | 2016-05-16 |  |  | Completed
|  | Preparation of test scripts | Venkat/Bhargav |  | 2016-05-02 | 2016-05-06 |  |  |  |  | 2016-05-16 |  |  | Completed
|  | Dry Run of the test cases | Venkat/Bhargav |  | 2016-05-02 | 2016-05-06 |  |  |  |  | 2016-05-16 |  |  | Completed
4 | Test cases identification & Crefo search | Identification of business cases for automation for RPCC | Gurinder |  | 2016-04-22 | 2016-04-22 | [7 empty] | WIP | 1. Test data sheets 2. Automation test scripts 3. Results and screenshots(if applicable) for the test cases
|  | Updation of manual test cases | Gurinder |  | 2016-04-25 | 2016-04-29 | [7 empty] | WIP
|  | Framework enhancement based on the identified scenarios(On Going process) | Venkat/Bhargav |  | 2016-05-02 | 2016-05-06 |  |  |  |  | 2016-05-16 |  |  | YTS
|  | Customization of the data sheet for automation | Venkat/Bhargav |  | 2016-05-02 | 2016-05-06 |  |  |  |  | 2016-05-16 |  |  | YTS
|  | Preparation of test scripts | Venkat/Bhargav |  | 2016-05-02 | 2016-05-06 |  |  |  |  | 2016-05-16 |  |  | YTS
|  | Dry Run of the test cases | Venkat/Bhargav |  | 2016-05-02 | 2016-05-06 |  |  |  |  | 2016-05-16 |  |  | YTS
5 | Test cases identification & Partner modification | Identification of business cases for automation for RPCC | Gurinder |  | 2016-05-02 | 2016-05-06 |  |  |  |  | 2016-05-16 |  |  | YTS | 1. Test data sheets 2. Automation test scripts 3. Results and screenshots(if applicable) for the test cases
|  | Updation of manual test cases | Gurinder |  | 2016-05-02 | 2016-05-06 |  |  |  |  | 2016-05-16 |  |  | YTS
|  | Framework enhancement based on the identified scenarios(On Going process) | Venkat/Bhargav |  | 2016-05-09 | 2016-05-27 |  |  |  |  | 2016-05-23 |  |  | YTS
|  | Customization of the data sheet for automation | Venkat/Bhargav |  | 2016-05-09 | 2016-05-27 |  |  |  |  | 2016-05-23 |  |  | YTS
|  | Preparation of test scripts | Venkat/Bhargav |  | 2016-05-09 | 2016-05-31 |  |  |  |  | 2016-05-23 |  |  | YTS
|  | Dry Run of the test cases | Venkat/Bhargav |  | 2016-05-09 | 2016-05-31 |  |  |  |  | 2016-05-23 |  |  | YTS
6 | Test cases identification & enhancement- Master data posting | Identification of business cases for automation for RPCC | Gurinder |  | 2016-05-02 | 2016-05-06 | [7 empty] | YTS | 1. Test data sheets 2. Automation test scripts 3. Results and screenshots(if applicable) for the test cases
|  | Updation of manual test cases | Gurinder |  | 2016-05-02 | 2016-05-06 | [7 empty] | YTS
5 |  | Framework enhancement based on the identified scenarios(On Going process) | Venkat/Bhargav |  | 2016-05-09 | 2016-06-17 |  |  |  |  | 2016-05-23 |  |  | YTS
|  | Customization of the data sheet for automation | Venkat/Bhargav |  | 2016-05-09 | 2016-06-17 |  |  |  |  | 2016-05-23 |  |  | YTS
|  | Preparation of test scripts | Venkat/Bhargav |  | 2016-05-09 | 2016-06-17 |  |  |  |  | 2016-05-23 |  |  | YTS
|  | Dry Run of the test cases | Venkat/Bhargav |  | 2016-05-09 | 2016-06-17 |  |  |  |  | 2016-05-23 |  |  | YTS
7 | Test cases identification & enhancement- partner consolidation | Identification of business cases for automation for RPCC | Gurinder |  | 2016-05-09 | 2016-05-13 |  |  |  |  | 2016-05-23
|  | Updation of manual test cases | Gurinder |  | 2016-05-09 | 2016-05-13 |  |  |  |  | 2016-05-23
|  | Framework enhancement based on the identified scenarios(On Going process) | Venkat/Bhargav |  | 2016-06-20 | 2016-07-15
|  | Customization of the data sheet for automation | Venkat/Bhargav |  | 2016-06-20 | 2016-07-15
|  | Preparation of test scripts | Venkat/Bhargav |  | 2016-06-20 | 2016-07-15
|  | Dry Run of the test cases | Venkat/Bhargav |  | 2016-06-20 | 2016-07-15
8 | Test cases identification & enhancement- Mandate Process and posting | Identification of business cases for automation for RPCC | Gurinder |  | 2016-05-16 | 2016-05-20
|  | Updation of manual test cases | Gurinder |  | 2016-05-16 | 2016-05-20
|  | Framework enhancement based on the identified scenarios(On Going process) | Venkat/Bhargav |  | 2016-07-18 | 2016-08-19
|  | Customization of the data sheet for automation | Venkat/Bhargav |  | 2016-07-18 | 2016-08-19
|  | Preparation of test scripts | Venkat/Bhargav |  | 2016-07-18 | 2016-08-19
|  | Dry Run of the test cases | Venkat/Bhargav |  | 2016-07-18 | 2016-08-19
9 | ReleaseDL16.B changes incorporation in automation & Closure | Execution of developed test cases in DL15.B SIT environment | Venkat/Bhargav |  | 2016-08-22 | 2016-09-03 | [7 empty] | YTS
|  | Test script should be changed according to the new changes implemented in ReleaseDL16.B | Venkat/Bhargav |  | 2016-09-05 | 2016-09-16
10 | Test execution in SIT Regression of DL16.B | Execution of automated testacase cases. Collating of test execution results and reporting Re-execution on need basis | Venkat/Bhargav |  | 2016-10-10 | 2016-10-20 | [7 empty] | YTS

## Selenium
S.No | Module |  | Activities | Resources | Activities Type | Resource Count | Hours per Resource | Hours(Actual) | Effort in days | Planned Start Date | Planned End Date | Revised Start Date | Revised End Date | Activity Status
1 | Automation Framework |  | Java Instalation and configuration | Venkatesh B | One Time | 1 | 2 | 2 | 0.25 | May/9/2016 | May/9/2016 | May/12/2016 | May/12/2016 | Completed
2 |  |  | Selenium Instalation and configuration | Venkatesh B | One Time | 1 | 2 | 2 | 0.25 | May/9/2016 | May/9/2016 | May/13/2016 | May/13/2016 | Completed
3 |  |  | Selenium Framework Archtecture Analysis\Discussion | Venkatesh B | One Time | 1 | 24 | 24 | 3 | May/10/2016 | May/12/2016 | May/16/2016 | May/18/2016 | Completed
4 |  |  | Selenium Framework Architecture Creation | Venkatesh B | One Time | 1 | 120 | 120 | 15 | May/13/2016 | June/02/2016 | May/19/2016 | June/08/2016 | Inprogress
|  |  | Creation of Reusable Selenium Object level Libraries | Venkatesh B | On Going | 1 | 60 | 60 | 7.5 | June/03/2016 | June/14/2016 | June/09/2016 | June/20/2016 | Inprogress
[7 empty] | Total Number of Days : |  | 26
S.No | Module | # Test Cases | Activities | Resources | Activities Type | Resource Count | Hours per Resource | Hours(Actual) | Effort in days | Planned Start Date | Planned End Date | Revised Start Date | Revised End Date | Activity Status
1 | Konzernview | 28 | Creation of Reusable Selenium Page level Libraries | Venkatesh B, Bhargav S | On Going | 2 | 80 | 40 | 5 | June/14/2016 | June/21/2016 | June/21/2016 | June/27/2016 | YTS
2 |  |  | Creation of automation scripts using Selenium | Venkatesh B, Bhargav S | On Going | 2 | 112 | 56 | 7 | June/22/2016 | June/30/2016 | June/28/2016 | July/06/2016 | YTS
3 |  |  | Creation of DataTable for Object Mapping | Venkatesh B, Bhargav S | On Going | 2 | 112 | 56 | 7 | July/01/2016 | July/11/2016 | July/07/2016 | July/15/2016 | YTS
4 |  |  | Creation of DataTable for Functional data mapping | Venkatesh B, Bhargav S , Gurinder | On Going | 3 | 56 | 18.6667 | 2.3333 | July/12/2016 | July/13/2016 | July/18/2016 | July/19/2016 | YTS
5 |  |  | Enhancement/modification of Automation Framework to cater the functionality | Venkatesh B, Bhargav S | On Going | 2 | 56 | 28 | 3.5 | July/14/2016 | July/19/2016 | July/20/2016 | July/25/2016 | YTS
6 |  |  | Identification of UPM test cases for automation | Venkatesh B, Bhargav S, Gurinder | On Going | 3 | 28 | 9.3333 | 1.1667 | July/20/2016 | July/20/2016 | July/26/2016 | July/26/2016 | YTS
7 |  |  | Application KT / walk through / navigation to understand the test cases | Venkatesh B, Bhargav S, Gurinder | On Going | 3 | 28 | 9.3333 | 1.1667 | July/21/2016 | July/21/2016 | July/27/2016 | July/27/2016 | YTS
8 |  |  | Daily Activity/Status Meeting | Venkatesh B, Bhargav S | On Going | 2 | 28 | 14 | 1.75 | June/14/2016 | July/21/2016 | June/21/2016 | July/27/2016 | YTS
9 |  |  | Weekly Activity/Status Meeting | Venkatesh B, Bhargav S | On Going | 2 | 5.6 | 1.7143 | 0.21429 | June/14/2016 | July/21/2016 | June/21/2016 | July/27/2016 | YTS
[7 empty] | Total Number of Days : |  | 29.131
S.No | Module | # Test Cases | Activities | Resources | Activities Type | Count | Hours per Resource | Hours(Actual) | Effort in days | Planned Start Date | Planned End Date | Revised Start Date | Revised End Date | Activity Status
1 | Admin Screens | 33 | Creation of Reusable Selenium Object level Libraries | Venkatesh B | On Going | 2 | 30 | 15 | 1.875 | July/22/2016 | July/25/2016 | July/28/2016 | July/29/2016 | YTS
2 |  |  | Creation of Reusable Selenium Page level Libraries | Venkatesh B, Bhargav S | On Going | 2 | 80 | 40 | 5 | June/26/2016 | Aug/01/2016 | Aug/01/2016 | Aug/05/2016 | YTS
3 |  |  | Creation of automation scripts using Selenium | Venkatesh B, Bhargav S | On Going | 2 | 66 | 33 | 4.125 | Aug/02/2016 | Aug/05/2016 | Aug/08/2016 | Aug/11/2016 | YTS
4 |  |  | Creation of DataTable for Object Mapping | Venkatesh B, Bhargav S | On Going | 2 | 66 | 33 | 4.125 | Aug/08/2016 | Aug/11/2016 | Aug/12/2016 | Aug/17/2016 | YTS
5 |  |  | Creation of DataTable for Functional data mapping | Venkatesh B, Bhargav S , Gurinder | On Going | 3 | 66 | 22 | 2.75 | Aug/12/2016 | Aug/16/2016 | Aug/18/2016 | Aug/22/2016 | YTS
6 |  |  | Enhancement/modification of Automation Framework to cater the functionality | Venkatesh B, Bhargav S | On Going | 2 | 66 | 33 | 4.125 | Aug/17/2016 | Aug/22/2016 | Aug/23/2016 | Aug/26/2016 | YTS
7 |  |  | Identification of UPM test cases for automation | Venkatesh B, Bhargav S, Gurinder | On Going | 3 | 33 | 11 | 1.375 | Aug/23/2016 | Aug/23/2016 | Aug/29/2016 | Aug/29/2016 | YTS
8 |  |  | Application KT / walk through / navigation to understand the test cases | Venkatesh B, Bhargav S, Gurinder | On Going | 3 | 33 | 11 | 1.375 | Aug/24/2016 | Aug/24/2016 | Aug/30/2016 | Aug/30/2016 | YTS
9 |  |  | Daily Activity/Status Meeting | Venkatesh B, Bhargav S | On Going | 2 | 24 | 12 | 1.5 | July/22/2016 | Aug/24/2016 | July/28/2016 | Aug/30/2016 | YTS
10 |  |  | Weekly Activity/Status Meeting | Venkatesh B, Bhargav S | On Going | 2 | 4.8 | 2.4 | 0.3 | July/22/2016 | Aug/24/2016 | July/28/2016 | Aug/30/2016 | YTS
[7 empty] | Total Number of Days : |  | 26.55
S.No | Module | # Test Cases | Activities | Resources | Activities Type | Count | Hours per Resource | Hours(Actual) | Effort in days | Planned Start Date | Planned End Date | Revised Start Date | Revised End Date | Activity Status
1 | International Address | 40 | Creation of Reusable Selenium Object level Libraries | Venkatesh B | On Going | 2 | 20 | 10 | 1.25 | Aug/24/2016 | Aug/24/2016 | Aug/31/2016 | Aug/31/2016 | YTS
2 |  |  | Creation of Reusable Selenium Page level Libraries | Venkatesh B, Bhargav S | On Going | 2 | 90 | 45 | 5.625 | Aug/25/2016 | Sep/01/2016 | Sep/01/2016 | Sep/08/2016 | YTS
3 |  |  | Creation of automation scripts using Selenium | Venkatesh B, Bhargav S | On Going | 2 | 60 | 30 | 3.75 | Sep/02/2016 | Sep/07/2016 | Sep/09/2016 | Sep/14/2016 | YTS
4 |  |  | Creation of DataTable for Object Mapping | Venkatesh B, Bhargav S | On Going | 2 | 40 | 20 | 2.5 | Sep/08/2016 | Sep/09/2016 | Sep/15/2016 | Sep/16/2016 | YTS
5 |  |  | Creation of DataTable for Functional data mapping | Venkatesh B, Bhargav S , Gurinder | On Going | 3 | 60 | 20 | 2.5 | Sep/12/2016 | Sep/13/2016 | Sep/19/2016 | Sep/20/2016 | YTS
6 |  |  | Enhancement/modification of Automation Framework to cater the functionality | Venkatesh B, Bhargav S | On Going | 2 | 30 | 15 | 1.875 | Sep/14/2016 | Sep/15/2016 | Sep/21/2016 | Sep/22/2016 | YTS
7 |  |  | Identification of UPM test cases for automation | Venkatesh B, Bhargav S, Gurinder | On Going | 3 | 30 | 10 | 1.25 | Sep/16/2016 | Sep/16/2016 | Sep/23/2016 | Sep/23/2016 | YTS
8 |  |  | Application KT / walk through / navigation to understand the test cases | Venkatesh B, Bhargav S, Gurinder | On Going | 3 | 30 | 10 | 1.25 | Sep/19/2016 | Sep/19/2016 | Sep/26/2016 | Sep/26/2016 | YTS
9 |  |  | Daily Activity/Status Meeting | Venkatesh B, Bhargav S | On Going | 2 | 19 | 9.5 | 1.1875 | Aug/24/2016 | Sep/19/2016 | Aug/31/2016 | Sep/26/2016 | YTS
10 |  |  | Weekly Activity/Status Meeting | Venkatesh B, Bhargav S | On Going | 2 | 3.8 | 1.9 | 0.2375 | Aug/24/2016 | Sep/19/2016 | Aug/31/2016 | Sep/26/2016 | YTS
[7 empty] | Total Number of Days : |  | 21.425
S.No | Module | # Test Cases | Activities | Resources | Activities Type | Count | Hours per Resource | Hours(Actual) | Effort in days | Planned Start Date | Planned End Date | Revised Start Date | Revised End Date | Activity Status
1 | Partner Creation | 10 | Creation of Reusable Selenium Object level Libraries | Venkatesh B | On Going | 2 | 0 | 0 | 0 | Sep/20/2016 | Sep/20/2016 | Sep/27/2016 | Sep/27/2016 | YTS
2 |  |  | Creation of Reusable Selenium Page level Libraries | Venkatesh B, Bhargav S | On Going | 2 | 20 | 10 | 1.25 | Sep/20/2016 | Sep/21/2016 | Sep/27/2016 | Sep/28/2016 | YTS
3 |  |  | Creation of automation scripts using Selenium | Venkatesh B, Bhargav S | On Going | 2 | 10 | 5 | 0.625 | Sep/22/2016 | Sep/22/2016 | Sep/29/2016 | Sep/29/2016 | YTS
4 |  |  | Creation of DataTable for Object Mapping | Venkatesh B, Bhargav S | On Going | 2 | 5 | 2.5 | 0.3125 | Sep/22/2016 | Sep/22/2016 | Sep/29/2016 | Sep/29/2016 | YTS
5 |  |  | Creation of DataTable for Functional data mapping | Venkatesh B, Bhargav S , Gurinder | On Going | 3 | 10 | 3.3333 | 0.41667 | Sep/23/2016 | Sep/23/2016 | Sep/30/2016 | Sep/30/2016 | YTS
6 |  |  | Enhancement/modification of Automation Framework to cater the functionality | Venkatesh B, Bhargav S | On Going | 2 | 5 | 2.5 | 0.3125 | Sep/23/2016 | Sep/23/2016 | Sep/30/2016 | Sep/30/2016 | YTS
7 |  |  | Identification of UPM test cases for automation | Venkatesh B, Bhargav S, Gurinder | On Going | 3 | 5 | 1.6667 | 0.20833 | Sep/23/2016 | Sep/23/2016 | Sep/30/2016 | Sep/30/2016 | YTS
8 |  |  | Application KT / walk through / navigation to understand the test cases | Venkatesh B, Bhargav S, Gurinder | On Going | 3 | 7.5 | 2.5 | 0.3125 | Sep/26/2016 | Sep/26/2016 | Oct/03/2016 | Oct/03/2016 | YTS
9 |  |  | Daily Activity/Status Meeting | Venkatesh B, Bhargav S | On Going | 2 | 5 | 2.5 | 0.3125 | Sep/20/2016 | Sep/26/2016 | Sep/27/2016 | Oct/03/2016 | YTS
10 |  |  | Weekly Activity/Status Meeting | Venkatesh B, Bhargav S | On Going | 2 | 1 | 0.5 | 0.0625 | Sep/20/2016 | Sep/26/2016 | Sep/27/2016 | Oct/03/2016 | YTS
[7 empty] | Total Number of Days : |  | 3.8125
S.No | Module | # Test Cases | Activities | Resources | Activities Type | Count | Hours per Resource | Hours(Actual) | Effort in days | Planned Start Date | Planned End Date | Revised Start Date | Revised End Date | Activity Status
1 | Optimised Partner Search | 3 | Creation of Reusable Selenium Object level Libraries | Venkatesh B | On Going | 2 | 0 | 0 | 0 | Sep/27/2016 | Sep/27/2016 | Oct/04/2016 | Oct/04/2016 | YTS
2 |  |  | Creation of Reusable Selenium Page level Libraries | Venkatesh B, Bhargav S | On Going | 2 | 6 | 3 | 0.375 | Sep/27/2016 | Sep/27/2016 | Oct/04/2016 | Oct/04/2016 | YTS
3 |  |  | Creation of automation scripts using Selenium | Venkatesh B, Bhargav S | On Going | 2 | 3 | 1.5 | 0.1875 | Sep/27/2016 | Sep/27/2016 | Oct/04/2016 | Oct/04/2016 | YTS
4 |  |  | Creation of DataTable for Object Mapping | Venkatesh B, Bhargav S | On Going | 2 | 1.5 | 0.75 | 0.09375 | Sep/27/2016 | Sep/27/2016 | Oct/04/2016 | Oct/04/2016 | YTS
5 |  |  | Creation of DataTable for Functional data mapping | Venkatesh B, Bhargav S , Gurinder | On Going | 3 | 3 | 1 | 0.125 | Sep/27/2016 | Sep/27/2016 | Oct/04/2016 | Oct/04/2016 | YTS
6 |  |  | Enhancement/modification of Automation Framework to cater the functionality | Venkatesh B, Bhargav S | On Going | 2 | 1.5 | 0.75 | 0.09375 | Sep/27/2016 | Sep/27/2016 | Oct/04/2016 | Oct/04/2016 | YTS
7 |  |  | Identification of UPM test cases for automation | Venkatesh B, Bhargav S, Gurinder | On Going | 3 | 1.5 | 0.5 | 0.0625 | Sep/28/2016 | Sep/28/2016 | Oct/05/2016 | Oct/05/2016 | YTS
8 |  |  | Application KT / walk through / navigation to understand the test cases | Venkatesh B, Bhargav S, Gurinder | On Going | 3 | 2.25 | 0.75 | 0.09375 | Sep/28/2016 | Sep/28/2016 | Oct/05/2016 | Oct/05/2016 | YTS
9 |  |  | Daily Activity/Status Meeting | Venkatesh B, Bhargav S | On Going | 2 | 2 | 1 | 0.125 | Sep/27/2016 | Sep/28/2016 | Oct/04/2016 | Oct/05/2016 | YTS
10 |  |  | Weekly Activity/Status Meeting | Venkatesh B, Bhargav S | On Going | 2 | 0.4 | 0.2 | 0.025 | Sep/27/2016 | Sep/28/2016 | Oct/04/2016 | Oct/05/2016 | YTS
[7 empty] | Total Number of Days : |  | 1.1812
S.No | Module | # Test Cases | Activities | Resources | Activities Type | Count | Hours per Resource | Hours(Actual) | Effort in days | Planned Start Date | Planned End Date | Revised Start Date | Revised End Date | Activity Status
1 | Crefo Search | 3 | Creation of Reusable Selenium Object level Libraries | Venkatesh B | On Going | 2 | 0 | 0 | 0 | Sep/29/2016 | Sep/29/2016 | Oct/06/2016 | Oct/06/2016 | YTS
2 |  |  | Creation of Reusable Selenium Page level Libraries | Venkatesh B, Bhargav S | On Going | 2 | 6 | 3 | 0.375 | Sep/29/2016 | Sep/29/2016 | Oct/06/2016 | Oct/06/2016 | YTS
3 |  |  | Creation of automation scripts using Selenium | Venkatesh B, Bhargav S | On Going | 2 | 3 | 1.5 | 0.1875 | Sep/29/2016 | Sep/29/2016 | Oct/06/2016 | Oct/06/2016 | YTS
4 |  |  | Creation of DataTable for Object Mapping | Venkatesh B, Bhargav S | On Going | 2 | 1.5 | 0.75 | 0.09375 | Sep/29/2016 | Sep/29/2016 | Oct/06/2016 | Oct/06/2016 | YTS
5 |  |  | Creation of DataTable for Functional data mapping | Venkatesh B, Bhargav S , Gurinder | On Going | 3 | 3 | 1 | 0.125 | Sep/29/2016 | Sep/29/2016 | Oct/06/2016 | Oct/06/2016 | YTS
6 |  |  | Enhancement/modification of Automation Framework to cater the functionality | Venkatesh B, Bhargav S | On Going | 2 | 1.5 | 0.75 | 0.09375 | Sep/29/2016 | Sep/29/2016 | Oct/06/2016 | Oct/06/2016 | YTS
7 |  |  | Identification of UPM test cases for automation | Venkatesh B, Bhargav S, Gurinder | On Going | 3 | 1.5 | 0.5 | 0.0625 | Sep/30/2016 | Sep/30/2016 | Oct/07/2016 | Oct/07/2016 | YTS
8 |  |  | Application KT / walk through / navigation to understand the test cases | Venkatesh B, Bhargav S, Gurinder | On Going | 3 | 2.25 | 0.75 | 0.09375 | Sep/30/2016 | Sep/30/2016 | Oct/07/2016 | Oct/07/2016 | YTS
9 |  |  | Daily Activity/Status Meeting | Venkatesh B, Bhargav S | On Going | 2 | 2 | 1 | 0.125 | Sep/29/2016 | Sep/30/2016 | Oct/06/2016 | Oct/07/2016 | YTS
10 |  |  | Weekly Activity/Status Meeting | Venkatesh B, Bhargav S | On Going | 2 | 0.4 | 0.2 | 0.025 | Sep/29/2016 | Sep/30/2016 | Oct/06/2016 | Oct/07/2016 | YTS
[7 empty] | Total Number of Days : |  | 1.1812
S.No | Module | # Test Cases | Activities | Resources | Activities Type | Count | Hours per Resource | Hours(Actual) | Effort in days | Planned Start Date | Planned End Date | Revised Start Date | Revised End Date | Activity Status
1 | Partner Modification | 29 | Creation of Reusable Selenium Object level Libraries | Venkatesh B | On Going | 2 | 0 | 0 | 0 | Oct/03/2016 | Oct/03/2016 | Oct/10/2016 | Oct/10/2016 | YTS
2 |  |  | Creation of Reusable Selenium Page level Libraries | Venkatesh B, Bhargav S | On Going | 2 | 43.5 | 21.75 | 2.7188 | Oct/03/2016 | Oct/05/2016 | Oct/10/2016 | Oct/12/2016 | YTS
3 |  |  | Creation of automation scripts using Selenium | Venkatesh B, Bhargav S | On Going | 2 | 21.75 | 10.875 | 1.3594 | Oct/06/2016 | Oct/06/2016 | Oct/13/2016 | Oct/13/2016 | YTS
4 |  |  | Creation of DataTable for Object Mapping | Venkatesh B, Bhargav S | On Going | 2 | 14.5 | 7.25 | 0.90625 | Oct/07/2016 | Oct/07/2016 | Oct/14/2016 | Oct/14/2016 | YTS
5 |  |  | Creation of DataTable for Functional data mapping | Venkatesh B, Bhargav S , Gurinder | On Going | 3 | 29 | 9.6667 | 1.2083 | Oct/10/2016 | Oct/10/2016 | Oct/17/2016 | Oct/17/2016 | YTS
6 |  |  | Enhancement/modification of Automation Framework to cater the functionality | Venkatesh B, Bhargav S | On Going | 2 | 14.5 | 7.25 | 0.90625 | Oct/11/2016 | Oct/11/2016 | Oct/18/2016 | Oct/18/2016 | YTS
7 |  |  | Identification of UPM test cases for automation | Venkatesh B, Bhargav S, Gurinder | On Going | 3 | 14.5 | 4.8333 | 0.60417 | Oct/12/2016 | Oct/12/2016 | Oct/19/2016 | Oct/19/2016 | YTS
8 |  |  | Application KT / walk through / navigation to understand the test cases | Venkatesh B, Bhargav S, Gurinder | On Going | 3 | 21.75 | 7.25 | 0.90625 | Oct/12/2016 | Oct/12/2016 | Oct/19/2016 | Oct/19/2016 | YTS
9 |  |  | Daily Activity/Status Meeting | Venkatesh B, Bhargav S | On Going | 2 | 8 | 4 | 0.5 | Oct/03/2016 | Oct/12/2016 | Oct/10/2016 | Oct/19/2016 | YTS
10 |  |  | Weekly Activity/Status Meeting | Venkatesh B, Bhargav S | On Going | 2 | 1.6 | 0.8 | 0.1 | Oct/03/2016 | Oct/12/2016 | Oct/10/2016 | Oct/19/2016 | YTS
[7 empty] | Total Number of Days : |  | 9.2094
S.No | Module | # Test Cases | Activities | Resources | Activities Type | Count | Hours per Resource | Hours(Actual) | Effort in days | Planned Start Date | Planned End Date | Revised Start Date | Revised End Date | Activity Status
1 | Partner Consolidation | 55 | Creation of Reusable Selenium Object level Libraries | Venkatesh B | On Going | 2 | 0 | 0 | 0 | Oct/13/2016 | Oct/13/2016 | Oct/20/2016 | Oct/20/2016 | YTS
2 |  |  | Creation of Reusable Selenium Page level Libraries | Venkatesh B, Bhargav S | On Going | 2 | 55 | 27.5 | 3.4375 | Oct/13/2016 | Oct/17/2016 | Oct/20/2016 | Oct/24/2016 | YTS
3 |  |  | Creation of automation scripts using Selenium | Venkatesh B, Bhargav S | On Going | 2 | 27.5 | 13.75 | 1.7188 | Oct/18/2016 | Oct/19/2016 | Oct/25/2016 | Oct/26/2016 | YTS
4 |  |  | Creation of DataTable for Object Mapping | Venkatesh B, Bhargav S | On Going | 2 | 27.5 | 13.75 | 1.7188 | Oct/20/2016 | Oct/21/2016 | Oct/27/2016 | Oct/28/2016 | YTS
5 |  |  | Creation of DataTable for Functional data mapping | Venkatesh B, Bhargav S , Gurinder | On Going | 3 | 41.25 | 13.75 | 1.7188 | Oct/24/2016 | Oct/25/2016 | Oct/31/2016 | Nov/01/2016 | YTS
6 |  |  | Enhancement/modification of Automation Framework to cater the functionality | Venkatesh B, Bhargav S | On Going | 2 | 27.5 | 13.75 | 1.7188 | Oct/26/2016 | Oct/26/2016 | Nov/02/2016 | Nov/02/2016 | YTS
7 |  |  | Identification of UPM test cases for automation | Venkatesh B, Bhargav S, Gurinder | On Going | 3 | 27.5 | 9.1667 | 1.1458 | Oct/27/2016 | Oct/27/2016 | Nov/03/2016 | Nov/03/2016 | YTS
8 |  |  | Application KT / walk through / navigation to understand the test cases | Venkatesh B, Bhargav S, Gurinder | On Going | 3 | 41.25 | 13.75 | 1.7188 | Oct/28/2016 | Oct/28/2016 | Nov/04/2016 | Nov/04/2016 | YTS
9 |  |  | Daily Activity/Status Meeting | Venkatesh B, Bhargav S | On Going | 2 | 12 | 6 | 0.75 | Oct/13/2016 | Oct/28/2016 | Oct/20/2016 | Nov/04/2016 | YTS
10 |  |  | Weekly Activity/Status Meeting | Venkatesh B, Bhargav S | On Going | 2 | 2.4 | 1.2 | 0.15 | Oct/13/2016 | Oct/28/2016 | Oct/20/2016 | Nov/04/2016 | YTS
[7 empty] | Total Number of Days : |  | 14.0771
Note on J8: Venkatesh B: Number of Days
Note on J22: Venkatesh B: Number of Days
Note on J37: Venkatesh B: Number of Days
Note on J52: Venkatesh B: Number of Days
Note on J67: Venkatesh B: Number of Days
Note on J82: Venkatesh B: Number of Days
Note on J97: Venkatesh B: Number of Days
Note on J112: Venkatesh B: Number of Days
Note on J127: Venkatesh B: Number of Days